## Sheet1
Northville City Council 2025-2026 Strategic Priorities Approved: February 20, 2025 Revised January, 2026 Updated: March 2025; June 2025; September 2025; December 2025; March 2026
I. | High Performing Government: Good Governance
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Fiscally responsible and accountable organization | 1. | Ensure financial solvency | a. | Increase pension funding to 120% | CM/Fin | Current valuation is at 104%. The next valuation will be available at the end of June 2025. The valuation for December 2024 has reached 116%. The next valuation will be available at the end of June 2026. The valuation dated 12/31/25 is expected to surpass the priority of reaching 120%. The results will be confirmed in the next valuation which will be issued in June 2026. The 12/31/25 valuation will be received next quarter.
|  |  |  | b. | Secure a AAA bond rating from S&P | CM/Fin | Bond rating will be received in May 2025. The City was awarded a AAA rating on May 21, 2025. COMPLETE.
|  | 2 | Pursue exterior funding sources for Capital Projects and administer program requirements | a. | Secure private donations for the completion of the Ford Field playground replacement project | CM/SP | Over $57,000 has been raised through the Patronicity crowd-funding platform for the project and additional funding from the community and local businesses continues to be pursued. The Patronicity fundraising program closed with total donations of $85,569 which was matched by $75,000 from the MEDC. An additional $23,000 was collected after the Patronicity campaign closed. The Northville Rotary Club and Northville Rotary Club Foundation have donated $100,000 to the playground replacement project and the Declan Carter Foundation continues its ongoing fundraising efforts for the park. A donation of $130,000 has been received from the Declan Carter Foundation and additional smaller amounts continue to be received. Plans exist for a letter campaign to reach out to potential business donors. March Update
|  |  |  | b. | Pursue TAP and NRTF grants for Ford Field east riverwalk | SP | In March, City Council approved a contract with OHM to develop plans for the riverwalk and draft a TAP grant for the project. A TAP grant application was submitted to SEMCOG on June 12, requesting $1.2 million for the project which has an engineer's estimate of $1.9 million dollars. TAP grants don't cover engineering costs and require a 20% match so this was the maximum level of funding that could be requested from this program. The city's TAP grant application was successful and $1.2 million have been secured for the trail extension. Staff will be developing a Natural Resources Trust Fund application for the April 1, 2026 grant submission deadline. The next phase of project engineering is underway including permitting, easement negotiations, and environmental due diligence. These are necessary to provide the required documentation for the NRTF application, which is due April 1, 2026 March Update
I. | High Performing Government: Good Governance (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  | 3. | Ensure services are provided in the most efficient and cost effective manner. | a. | Begin utilizing electronic plan review software and integrate it with BS&A Cloud | CD | In January 2025, staff held the e-Plan Review kick-off meeting. In March 2025, Council approved BS&A Cloud improvements to the Community Development module to facilitate the software implementation. This project will begin on March 31, with the intention to send ePlanSoft what they need for implementation by April 11. Updates to the Community Development module of BS&A Cloud have been completed. e-Plan review software training began June 24 and will continue through July. Integration of the e-Plan review software with BS&A Cloud, and user training, is ongoing. Munivate is assisting with the integration effort. The target for completion is December. The Department went live with the e-Plan review software on December 15. User training is expected to conclude in January. COMPLETE.
|  |  |  | b. | Explore options for online submissions of applications and payments for licenses and permits issued by the Clerk’s Department. | CK | This project is on hold during the Clerk staff transition. No update this quarter. No update this quarter. No update this quarter. March Update
|  |  |  | c. | Complete the migration from .mi.us to .gov | FIN | the vendor is working on the migration. Expected completion next quarter.
|  |  |  | d. | Establish a cybersecurity incident response plan and team | FIN | The plan is complete. The CIRT team will hold an initial meeting next quarter.
|  | 4. | Provide for stable revenue streams | a. | Ensure financial sustainability of Allen Terrace in consideration of long term capital needs | AT | No update this quarter. Will begin working on Capital Plan with HC President during summer break Meeting with HC President was postponed until late fall Capital Plan is a rough draft and meeting with HC President still needed March Update
|  |  |  | b. | Evaluate fees and charges and recommend adjustments as appropriate | All | Municipal Analytics has been contracted to conduct a user fee study of the various programs and services offered by the City. The first kick off meeting was held the week of March 24 and the study is expected to be completed in the 2nd quarter. Municipal Analytics has completed data collection and will be meeting with staff in July. The study is expected to be completed in August. The recommended rates were presented to City Council in September 2025. All rate changes are effective October 1, 2025. COMPLETED
I. | High Performing Government: Good Governance (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
B. | Responsive and accessible service | 1. | Provide a variety of ways to inform citizens of important City Information | a. | Finalize and implement a communications plan, including metrics. | CM/ COM | Staff is working with a consultant to implement the communications plan. More information is being distributed to the community in various ways. Facebook statistics from first quarter (Jan 1 – March 31) to second quarter (April 1 - June 20) this year demonstrate success in this area. Facebook posts were increased from 98 last quarter to 105 this quarter. Facebook Engagement increased 28.6% (7.36% to 9.47%) and FB Followers increased 5.2% (from 3205 to 3372). Page and Profile Impressions increased by 26.7% (from 139,709 to 175,715) while Page and Profile Reach increased by 8.9% ( from 110,933 to 120,810). Most impressively, comments on FB posts increased by 96.6% (from 116 comments to 228) and reactions to our FB posts increased 169% (from 705 to 1893). Facebook statistics from the second quarter ( April 1 - June 30) to third quarter ( July 1 - September 25) show continuous growth. Facebook followers increased by 26% ( 3,399 to 4,283). Our page impressions increased by 228% (from 207,042 to 678,820). Our post engagement rate is 7.55% (down 16.1% from 9% in the previous quarter, but this is not a concern). Our post impressions increased by 188% ( from 196,123 to 563,994). Our post likes increased 128% (from 1,704 to 3,883.) Two of our top three posts included information about the Daylighting of the Rouge River. Facebook analytics highlight growth in the fourth quarter (October 1- December 19). Facebook followers increased by 13.1% (4,387 to 4,962). Post engagement rate also increased 22.7% (from 7.48% to 9.18%). Out post impressions were 336,999. As we do not pay for advertising at this time, this is a great number. Out post shares are down from 737 to 325, and likes are down 3,316 from 4,927. Please note that "down" doesn't mean negative. Engagement depends on news cycle, positive/negative stories, downtime, slower seasons, etc. March Update
|  |  |  | b. | Evaluate and restructure eNewsletter and other electronic communication methods | CM/ COM | The eNewsletter now has its own "Council Recap section" and there has been some modifications to the design to make it functional: removal of button-like section at the top that may confuse people as they are not buttons, and adding in a new section that highlights exciting news such as staff accomplishments, new hires, awards, etc.. Modifications were made to the City News newsletter for better flow and readability. There are 2,628 contacts on the City News list. There is a social media campaign in place to prompt community members to sign up The city newsletter is sent out weekly. Modifications are complete. Staff will continue to monitor electronic communications and adjust as needed. COMPLETED
I. | High Performing Government: Good Governance (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | c. | Assess the city website and re-vamp. | CM/ COM | No update this quarter A website redesign team has been formed. The RFP for website redesign was made public on June 10, 2025 and will close on July 31, 2025. We are anticipating the launch of a new website will take about 9 months in total. The city received 24 proposals from possible vendors. We have narrowed it down to six. The website team is meeting the first week of October to narrow down the choices to interview 3. The interviews will take place in October and we will choose a new vendor after interviews have taken place. A contract with new vendor CivicPlus has been signed and submitted. The website redesign is a 9-month process which will implemented throughout 2026. March Update
|  |  |  | d. | Evaluate the use of Zoom for public comment during City Council meetings | CM | Beginning with the March 17 City Council meeting, viewers were given the opportunity to offer public comment via calling in. This method will be used instead of Zoom. COMPLETE
|  |  |  | e. | Develop a communications program to distribute information about Sheldon and 7-mile roundabout construction |  | To be implemented next quarter. The City has scheduled an in-person community meeting for the end of July to share information about the project and schedule. Roundabout construction updates are distributed bi-weekly by the project engineers. Communications staff has updated the city website with important information and has created a social media campaign to encourage residents to sign up for the text and email updates. Bi-weekly construction updates continued throughout construction and social media posts were sent at key times as needed. The update list will be re-activated in the spring when construction resumes. March Update
|  | 2. | Improve procedures for communicating with residents during emergency situations | a. | Develop emergency communications templates and practices | CM/ COM | Drafts of social media "important information" posts have been completed. Press release templates for emergency communications are in progress. Press release template has been created and is ready to use. Courtney is working with Herta to complete emergency templates for fires, floods, etc. Communications continues to work with Herta to complete information related to emergency plans. Communications continues to work on emergency plans. March Update
I. | High Performing Government: Good Governance (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | b. | Increase enrollment and use of Nixle as appropriate | COM/ POL | Created a social media campaign to increase Nixle Enrollment which had 3,222 contacts this quarter. 30 announcements were made: 13 advisory messages related to road closures and water main breaks and work; 15 alert messages related to weather, and 2 Community messages related to inter storm watches. Posting regularly on social media to enlist new users. We have a total of 3,274 contacts which is a growth of 52 new users. 30 Nixle announcements were sent out including: 3 community messages, 14 weather alerts, and 13 advisory messages that include weather and road closers/traffic alerts. We have a total of 3,297 Nixle contacts, which is a growth of 23 new users. 36 Nixle alerts were sent out this quarter: 3 community messages, 11 advisory messages, and 21 alert messages. We have a total of 3,343 Nixel Contacts which is a growth of 46 new users. Communication specialist sent city interns to distribute flyers containing information on how to subscribe. 17 Nixle alerts were sent out this quarter: 3 Alert messages, and 14 Advisory messages. March Update
|  |  |  | c. | Develop a Snow and Ice Emergency Ordinance and review the policy for Snow Removal in neighborhoods | POL/ DPW | Existing ordinances are being researched and reviewed. No Update at this time. Ordinance research and review still in process. Proposed updates to the ordinance will presented to City Council in November 2025. City Council approved revisions to the Ordinance in December, 2025. COMPLETE
|  | 3. | Promote two-way communication with citizens | a. | Host open house meetings as appropriate. | All | No open house or informational meetings have been held this quarter but a Constant Contact group has been developed to provide updates associated with the Cady Water main to interested persons, and a webpage was created to provide information on the Serenity Point construction to the public. A community meeting was held on June 12 for the Gateway project. Approximately 20 people were in attendance. A Playground Community Design event was hosted on Saturday August 16 and was well attended by children and adults alike. A neighborhood preconstruction meeting was held for the Eaton Drive Reconstruction and a community Roundabout Construction meeting was held prior to the beginning of construction. A Neighborhood Preconstruction Meeting was held for the Booster Station Project and a neighborhood input meeting was held to receive input for the design of the River Street reconstruction project. A community open house was held on February 24, for Ford Field Park projects and a Downtown Stakeholders meeting held on February 25 to discuss proposed Main Street improvements.
I. | High Performing Government: Good Governance (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | b. | Assess current phone system: people and technology to promote better customer service | CM/ CK | Proposed phone tree drafted for review and department head input The proposed phone tree is being updated based on input received and will be redistributed for additional input prior to implementation. No update this quarter. No update this quarter March Update
|  |  |  | c. | Continue offering Coffees-with-Council. | CM | A schedule will be developed this upcoming quarter for the 2025 Coffees-with-Council. The summer Coffees-with-Council have been scheduled, with the first being held on June 12 at Sweet Brew Cafe. Approximately 10 people were in attendance. Coffees with Council were hosted by Genitti's on July 17, and by The Sports Den on August 21. Attendance remains consistent. No Coffees with Council have been held this quarter. March Update
|  |  |  | d. | Explore options for conducting a community survey | CM | No update this quarter No update this quarter. Will evaluate cost and options, and consider feasibility in 2026 March Update
|  |  |  | e | City Manager meet with neighborhoods and attend community interest meetings. | CM | City Manager attended several chamber activities, meetings with local businesses, also attended Senior luncheons held this quarter at the community center City Manager attended several community meeting including a neighborhood annual meeting and coffee with Council. Attended the Beautification awards luncheon, two Coffees with Council, and the Playground and Round-about Public Meetings. Attended the Chamber of Commerce annual meeting and several Chamber sponsored after hours mixers. Attended the Celebrate the Season seniors luncheon and participated in the Holiday Lighted Parade. Attended Chamber of Commerce coffee connection at Northville Pickleball Club
C. | Quality and stable work force | 1. | Meet or exceed industry standards for professional performance | a. | Complete re-accreditation of Police Department | POL | A re-accreditation mock onsite has already been completed. Our re-accreditation on-site will take place the week of May 5th, 2025. We are awaiting a formal date from MACP. There are a couple of things we need to take care of before the official reaccreditation date. The re-accreditation on-site visit was conducted in May as planned and the city was successfully accredited on Tuesday, June 24. The accreditation is valid for three years, through June 30, 2028. COMPLETED
I. | High Performing Government: Good Governance (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | b. | Support accreditation of the Parks and Recreation Department | CM | Goals are being compiled to align them with the strategic plan and to provide guidance to the task force that will be formed next quarter to guide the CAPRA (Council of Accreditation of Park and Recreation Departments) accreditation process. The Accreditation Team has been formed and held two meetings to develop standards and progress tracking measures. Several team meetings have been held to identify and assign tasks. A list has been developed of plans, documents and policies that are required for accreditation. The Department is aiming for accreditation in 2027 or 2028. Work is ongoing. March Update
|  |  |  | c. | Evaluate staffing levels and needs to ensure right-level staffing, including cost effectively using consultants and/or contracted labor | CM | Continuing to review current contracted services for cost and efficiency. Completed labor negotiations with in-house staff. Will continue to monitor and adjust as needed. Interviews were conducted for an Assistant Fire Chief but the chosen candidate declined the employment offer so evaluation of this position continues. Review was conducted of Code Department needs and adjustments made in duties to account for current needs. March Update
|  | 2. | Support continuing staff development | a. | Ensure all leadership staff undergo emergency management training to an intermediate level or higher | CM | Information has been distributed to senior staff about how to access the online Emergency Management Institute training modules. Training progress will be reported in upcoming quarterly updates. No update this quarter. In addition to the two Chief's, three leadership staff have completed the four introductory training levels and one staff has completed the first training. No additional staff have completed emergency trainings this last quarter. All leadership staff participated in a full-day leadership development activity on December 12. March Update
D. | Open and transparent governance | 1. | Ensure public duties are conducted with integrity | a. | Research and recommend a comprehensive ethics ordinance and a conflict of interest code of conduct | CM | No update this quarter Anticipated for 2026. Anticipated for 2026 The City Clerk has gathered sample ordinances from similar communities and is crafting a draft ordinance which will be forward to Council when available. March Update
|  | 2. | Provide for efficient access to public records | a. | Digitize Community Development files and evaluate options for an electronic storage platform | CD/CK | The Community Development Director and City Clerk will explore electronic storage options and bring recommendations to Council later this calendar year. Staff is researching options for digitizing records and electronic record management solutions. Community Development staff has begun boxing files. The Clerk has communicated with third-party document management companies, and may develop a RFP for scanning services. The Clerk has gathered information from businesses to assist with the digitizing. Next steps will depend on timing and the availability of funding. March Update
I. | High Performing Government: Good Governance (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  | 2. | Provide for efficient access to public records | a. | Digitize Community Development files and evaluate options for an electronic storage platform | CD/CK | The Community Development Director and City Clerk will explore electronic storage options and bring recommendations to Council later this calendar year. Staff is researching options for digitizing records and electronic record management solutions. Community Development staff has begun boxing files. The Clerk has communicated with third-party document management companies, and may develop a RFP for scanning services. The Clerk has gathered information from businesses to assist with the digitizing. Next steps will depend on timing and the availability of funding. March Update
|  |  |  | b. | Explore options for record retention modernization and expansion of electronic document management | CK | This project is on hold during the Clerk staff transition. No update this quarter. No update this quarter. Staff is evaluating the option of combining this work with the electronic storage platform project. March Update
II. | Vibrant Economy and Development
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Balanced parking system | 1. | Provide adequate parking to support visitor, business and resident needs | a. | Evaluate the Parking Study and provide recommendations to address system needs. | DPW/ DDA/CD | Received a proposal from Fishbeck to do additional work per Council's request. Will be evaluating the proposal and providing Council with recommendations next quarter. Based on city feedback, Fishbeck completed the revisions to the study that were within their project scope but will not be conducting more extensive revisions due to the cost. The study has been received and will be used to inform future recommendations. COMPLETE
|  |  |  | b. | Implement a parking enforcement program that supports proper system utilization | DDA/ POL | Enforcement of timed parking began on March 10, 2025. Several pre-meetings were conducted with business owners to announce the enforcement. Warning are given for first time violators of timed parking. Visual inspections of timed parking areas shows enforcement is creating greater turnover. Monitoring/enforcement continuing. This quarter 160 warning tickets have been issued and 154 violation have been issued, for a total of 314 citations. More consistent turnover continues to be observed. Parking Enforcement continuing. 194 parking violations were issued this quarter with 101 of the violations being warnings. The enforcement continues to show turnover of downtown parking spaces. Timed enforcement continues. 140 violations were issued this quarter with 59 of the violations being written as warnings. The enforcement continues to allow for the turnover of downtown timed parking spaces. It should be noted that as of January 1, 2026, all first offenses for timed parking will be issued as warnings. An on-street overnight parking enforcement moratorium was implemented for December 20 - January 5 to accommodate overnight holiday visitors. March Update
II. | Vibrant Economy and Development (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
B. | Resilient and vibrant downtown | 1. | Provide a range of programs to support seasonal activation of the downtown | a. | Develop strategic partnerships to expand program offerings in the downtown | DDA | Entered a joint partnership with the Chamber of Commerce to provide a new 33-concert series Music-in-the-Ville implemented in May 2025. Increased concert series to 45+, with jazz on Thursdays at Town Square, programmed Wednesday evenings on Center Street with third party vendor recreation tournament. Closing out seasonal summer programming and starting October programming with the launch for Skeletons are Alive. A comprehensive street closure special event application was developed for October emphasizing the importance of stakeholder coordination (DDA/City/Chamber/NCBA /Private entities). Work continues on finalizing an annual special event calendar and street closure schedule. Development of strategic partnership is ongoing, an example of which is the Downtown Business Associate presenting the Chili In the Ville this year. March Update
|  |  |  | b. | Compile downtown business metrics and launch an economic health tool | DDA | This project is on hold during the DDA Director Transition DDA has initiated Placer AI analysis services through SEMCOG to collect data on district activity (trips, traffic volume). Considering Michigan Main Street for technical assistance, free through MEDC, for real estate management/inventory. DDA staff engaging Michigan Downtown Association resources for best practice recommendation. SEMCOG delivered reports for trip metrics showing consistent traffic into the downtown over recent consecutive years. A regional impact report has been requested for the LIV golf tour event in August. Michigan Main Street overview and onboard with DDA's EDC Committee and DDA Board in October 2025. DDA has engaged MEDC's Michigan Main Street. Initial Board orientation training has been completed (more than 24 hours in total). DDA Board has a Strategic Vision Retreat on January 21. March Update
II. | Vibrant Economy and Development (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  | 2. | Ensure downtown infrastructure is attractive and safe for all visitors | a. | Pursue funding for curbless streets in the downtown and streetscape improvements in other areas | DDA | Awaiting the results of the RAP 3.0 grant applications. The RAP 3.0 grant was unsuccessful so Grissim Metz has been contracted through DDA to assess conditions and recommend improvements to portions of Main Street adjacent to Town Square. Design Committee engaged. DDA staff working with City administrative team, OHM , GMA, to understand work phasing applicable to funding strategy. DDA Executive Comm meeting to share options for financing downtown capital projects through DDA debt service allocation to City General Fund. Options in development, communicated concurrently to both DDA Board and City Council. DDA has secured an intergovernmental loan from City to fund capital projects downtown including reconstruction of Main Street between Center and Hutton, and the extension of a tabletop plaza at Town Square in FY2026. DDA has secured a SEMCOG TAP grant to fund Cady Street Pedestrian Connection in the next fiscal year. March Update
|  |  |  | b. | Explore expanding the safe street closure area for special events to allow greater flexibility in set-up, layout, etc. | DDA/ POL | Increased safety protocols for street closures are being examined and will be implemented as needed to ensure vehicles can't enter closed areas. Staff will be evaluating the purchase of mobile barricades in the future for this purpose. Monitoring/Used additional police and DPW vehicles for event closure hardening of the Art Festival. Western Wayne is providing Meridian barricades to the city to use for the 4th of July Parade. Vehicles and barricades continue to be used for special events for street closures and hardening . Discussion is being had regarding the possibility of purchasing and installing bollards at Wing/Main and Center/Mary Alexander. This is the common footprint for special events. The cost between bollards and Meridian Barricades will be examined to see what works best in our situation. Currently reviewing the special event policy and procedure across all departments to improve process efficiency and clarity. March Update
II. | Vibrant Economy and Development (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | c. | Repair, replace, and/or augment downtown street furnishings to assure they are safe and well maintained. | DDA | Administrative and maintenance staff conducted a condition inspection of all downtown furnishings and are securing quotes from furnishing providers to replace items as needed. DDA is using the stronger DPW partnership and outside vendors to maximize resources and ensure street furnishings are maintained in the most efficient and effective manner. Downtown conditions are evaluated frequently and several areas have been identified for augmentation by contracted resources (i.e. cleaning and painting the Comerica Community Connection). DDA allocating budget toward multiple projects for immediate execution (arborist services, Town Square hardscape and plantscape maintenance and upgrades, including electrical and masonry cleaning and replacement) and also near future execution in FY2026-28 (band shell repair and maintenance, fountain reconstruction, Design Development of Cady Connection improvements and streetscape planning for Cady Street). A 90 day pilot program with Throne has been implemented, installing a free, ADA-accessible public restroom downtown. Town Square furnishings replacement and upgrade scheduled for Spring 2026, as budgeted and specified through inventory analysis with Grissim Metz in 2025. March Update
|  |  |  | d. | Evaluate options for sidewalk snow removal in downtown and recommend to DDA | DDA/ DPW | No update this quarter No update this quarter No update this quarter Multiple methods of snow removal in practice. Private property owners remain responsible for ROW fronting property. Costs to conduct downtown sidewalk snow in-house or via contract are cost prohibitive. No further evaluation is needed. COMPLETE
|  | 4. | Promote quality communication with business owners | a. | Utilizing the new Communications Specialist, upgrade DDA Newsletter and increase viewers/readers for DDA communications. | DDA/CM | DDA staff is actively working with new Communications Director to implement new marketing priorities and positive messaging for the DDA. DDA and Communications Director have met with Herta to understand and maximize shared resources. DDA will share growth analytics dashboard for socials engagement and analytics at June Board meeting. DDA engaging with NCBA and reorganizing Marketing Committee structure to focus on district promotion. DDA hosted larger community steering meeting in August to capture communications for October through year-end. DDA hosted social media workshop in two sessions with Herta Communications, investing in downtown businesses to upgrade user content and share best practices for maximizing downtown community, place-based promotion. Integration of new social media content strategy and other communications are included in year end impact report. There have been major engagement and reach gains across all platforms. March Update
II. | Vibrant Economy and Development (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  | 5. | Improve downtown connection | a. | Improve alleyways to connect downtown businesses with rear parking, | DDA | Implementing a joint partnership with Orin Jewelers to provide landscaping and beautification for the alley behind their building. Decided on seasonal plantings for the downtown with Begonia Brothers Beginning incremental improvements with planting bed maintenance, coordinating with City Special Projects to understand context of grant/City/DDA-funded capital projects at Gateway into Ford Field and Cady Connection. Reviewing shared position (DDA/DPW) outcomes at end of season; postings are live for two part-time positions focusing on downtown maintenance. Orin's alley evaluated and investment postponed until Spring 2026. Prioritized budget toward lighting Main Street trees, in agreed preference with adjacent business. March Update
|  |  |  | b. | Improved connection between historic downtown and new Northville Downs neighborhood to south. | CM/ DDA/ SP | Met with the DDA Design Committee chair to develop ideas and plans, to be reviewed by the DDA DDA engaging with Grissim Metz to inventory and identify asset maintenance conditions for connection from Town Square south to Cady Street. GMA to prepare schematic design for contiguous accessibility, including existing vertical chase, and Hutton Street connection, into Downs. GMA has been authorized to prepare Design Development documents docs detailing cost and construction options for improved connections between downtown and the Downs neighborhood. This will include a funding/phasing strategy. DDA has secured a SEMCOG TAP grant to fund Cady Street Pedestrian Connection in the next fiscal year. March Update
III. | Strong Neighborhoods: Strong, Safe, Diverse Communities
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Stable neighborhoods | 1. | Provide clear priorities for land use | a. | Evaluate implementation of the updated Historic District Design Guidelines, and if necessary, draft amendments in conjunction with SHPO | CD | The Historic District Commission (HDC) has been utilizing the updated Design Guidelines since adoption last summer and are becoming more comfortable with the guidelines as familiarity increases. Staff will continue to monitor the guidelines over time to identify if modifications are needed. Staff does not anticipate an update to the guidelines will be necessary this calendar year. It is not anticipated that guideline updates will be needed. COMPLETE
III. | Strong Neighborhoods: Strong, Safe, Diverse Communities (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | b. | Review ordinances and recommend updates to modernize land use policies | CD | The Planning Commission will hold a public hearing in April on an amendment to the Zoning Ordinance to alter the regulations for residential air conditioning condensers, heat pump units, and generators. On June 2, City Council approved the second reading and adoption of a Zoning Ordinance amendment to alter the regulations for residential air conditioning condensers, heat pump units, and generators. On June 16, City Council approved the second reading and adoption of an amendment to the Code of Ordinances to align the ordinance's lot split approval authority provisions with current State law. The Planning Commission will hold a public hearing on July 15 on an amendment to the Zoning Ordinance to establish regulations for rooftop uses in certain zoning districts. A Rooftop Uses ordinance was adopted on September 4. Council approved the first reading of Zoning Ordinance amendments to revise the R-3 District density allowance and parking lot landscape requirements; the second reading is scheduled for October 6. A subcommittee of the Planning Commission reviewed Zoning Ordinance provisions related to hardscape/impervious surface coverage in residential districts. The subcommittee presented its findings to the PC on August 19, and the PC requested staff draft Zoning Ordinance amendments for review by the PC. Staff and two members of the Planning Commission are developing recommendations related to hardscape and impervious surface coverage in residential districts. An update is planned for presentation to the full Commission in January. On December 16, the Downtown Development Authority (DDA) Board and the Planning Commission discussed the draft Central Business District first-floor uses ordinance at their respective meetings. The DDA Board unanimously approved a motion supporting advancement of the draft language through the ordinance amendment process. The Planning Commission requested additional information, which staff intends to provide early next year. March Update
|  |  |  | c. | Revise the sign ordinance so it is content neutral | CD | A 2015 U.S. Supreme Court decision ruled that sign ordinances cannot have different requirements for signs based on their content and the city sign ordinance will need to be amended to comply with this ruling. Staff is researching compliant sign ordinances in preparation of amending the City's sign ordinance. Ordinance research and review still in process. Ordinance research and review still in process. A draft ordinance was discussed at the December 16 Planning Commission meeting and approved a motion to schedule a public hearing on the draft ordinance at a future meeting. Commissioners expressed the need for a comprehensive rewrite of the sign ordinance. Staff is evaluating options to address this efficiently as part of the current effort. March Update
III. | Strong Neighborhoods: Strong, Safe, Diverse Communities (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | d. | Update City Ordinances related to City Parks and reservation of public space | CD | Currently “Publicly owned and operated libraries, parks, parkways and recreation facilities and publicly owned historical village” are special land uses in an R-1 District. Staff is preparing a proposed ordinance amendment to make these uses permitted by right and will bring this item forward for formal consideration in 2025. Ordinance research and review is in process. Ordinance research and review is in process. The sign ordinance updates referenced above include exemptions for City signage, including park signage. This will provide flexibility when updating signage to reflect the new Parks and Recreation brand. March Update
|  |  |  | e. | Begin a review and update of the Master Plan in mid-2026 | CD | This project is expected to begin in mid-2026 No progress this quarter Staff has discussed partnering with the DDA to include an East Cady Street sub-area plan as part of the City's Master Plan update, which is still slated to begin in mid-2026. Combining efforts could provide cost savings for both the City and DDA. More progress is anticipated on this item in mid-2026. March Update
|  | 2 | Ensure residents' safety and security | a. | Evaluate establishing a rental registration ordinance and program, including short term rentals (Vrbo, AirBnb, etc.) | CD | Met with an Airbnb policy associate to discuss considerations of regulating short-term rentals as part of a rental registration program. This information will be used to inform a rental regulation program for Council's consideration. Ordinance research and review is in process. Staff has begun preparing a draft ordinance. Work on this item progresses as time is available. March Update
|  |  |  | b. | Implement lead service line program in accordance with EGLE requirements, including inventory of service lines. | DPW | Will be proposing a contract award with 310 Contracting to perform hydro-excavating to identify material types for water service lines. The work will be performed this calendar year. A Contract was awarded to 310 Contracting on April 7 for the work, and a preconstruction meeting was held June 30. There are service lines within the social district so a work schedule is being developed to coordinate with the downtown schedule. Also in accordance with EGLE requirements, a letter was distributed to all water customers who have service lines that are galvanized or of unknown material notifying them that they could possibly have lead lines. Contractor 310 has started the service line inventory. Our contractor, 310 Group, continued to inspect and verify the lead service lines throughout the community and compline a comprehensive inventory. Work has been halted for the winter and will resume in spring. March Update
III. | Strong Neighborhoods: Strong, Safe, Diverse Communities (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | c. | Explore emergency water connections with neighboring communities | DPW | No update this quarter The City of Novi has agreed in concept to an intergovernmental agreement committing both agencies to providing water support to each other during an emergency. An agreement will be drafted for approval of both Councils later this year in preparation for installation of the emergency water connection, which is included in 2026 watermain and street program plan. Working on Draft agreement and Design A draft agreement with the City of Novi is under review by the city Attorney. March Update
|  |  |  | d. | Develop and implement emergency exit maps and protocols for Allen Terrace | AT | Maps have been designed and should be distributed by May Maps are ready. We are waiting on AED machines. Will schedule a training/meeting with Fire once we receive the machines. Applied for a grant that would fund the CPR/AED classes. AED machines and maps will be hung after renovations are completed end of October/early November Residents had a fire safety class. AED/CPR class was canceled due to lack of participation. Every apartment and hallway has the new fire safety maps and AED machines are on each floor. COMPLETE
B | Sustained population | 1. | Provide for programs and services that support aging in place | a. | Consider allowing accessory dwellings in appropriate zoning districts | CD | This would be a major policy change and information on this land use is being prepared for review with the Planning Commission. Ordinance research and review is in process. Staff has begun preparing information in order to begin discussion with the Planning Commission. This land use will be evaluated as part of the Master Plan update. Progress on this item may not advance until that time, given the number of other ordinance amendments currently underway. March Update
|  |  |  | b. | Continue to support the diverse senior activities being conducted through Parks & Recreation | CM | City Manager attended the Taste of Italy Senior luncheons at the Community Center, supported by the Council and staff. No update this quarter Parks and Recreation hosted a senior luncheon in September. The City Manager attended the Celebrate the Season seniors holiday luncheon. The Parks and Recreation Department continue to provide quality programs and services to the communities older adults. From 2023 to 2024, Community Center visitors rose 17.8% and from 2021 to 2024 there was a nearly 45% increase in visitors. City Manager attended the St. Patrick's day luncheon at the Senior Center
III. | Strong Neighborhoods: Strong, Safe, Diverse Communities (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  | 2. | Support approved development projects | a. | Maintain oversight of developments | CD/ SP | Monitoring of the Downs development continues. Regular meetings are held with Toll Brothers, HP, and Sachse to monitor construction progress and ensure positive communication. The developments at 711 N. Center and on the old Pizza Cutter continued to be monitored, as do residential new builds and/or rebuilds at 340 N. Center, on the empty lot on Carrington, on the 500 block of Randolph and the 800 block of W. Main Bi-weekly update meetings with Downs developers have continued as have bi-weekly internal coordination meetings. Construction has resumed on the Delano project and the rebuild at 340 N. Center Street. Bi-weekly update meetings continue with Downs developers and additional meetings are scheduled as needed to address specific issues (groundwater control, soil erosion issues, site coordination, etc.). Oversite continues on other development project including the Delano project, 711 Center, and 340 N. Center Development oversite continues as mentioned above. The Police Department continues to monitor and do their best to manage unauthorized use of the River Park but without property line fencing, its not feasible to eliminate all use. March Update
|  | 3. | Implement programs and services that support a safe school system | a. | Conduct school-specific public safety trainings and services | POL | March Update
|  |  |  | b. | Evaluate the School Resource Officer contract and facilitate renewal | POL | Met with Northville School District representatives on Feb. 13
C | Strong Community | 1. | Promote welcoming neighborhoods | a. | Produce and distribute Welcome packets to new residents | Comm | No progress this quarter A team will be convened in July to review existing programs and define desired outcomes from the project. Team includes staff from Communications, Special Projects, and DDA, and representatives from the Sustainability Team, Northville Rotary and the Chamber of Commerce. An initial meeting was hosted to discuss what is currently being done to welcome new residents to the City and brainstorm about what a new resident welcome packet might entail. All parties of the meeting are conducting research and collecting resources that could be used in the process. No new progress this quarter. March Update
III. | Strong Neighborhoods: Strong, Safe, Diverse Communities (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  | 2. | Implement programs that reinforce the unique community that is Northville | a. | Evaluate establishing a signage program for historic homes/historic district, including interpretive signs where appropriate and an online resource | CD/ CK/ SP | Met with members of the Northville historical society last quarter to discuss interest in such a program. No progress was made this quarter The Bicentennial Committee is evaluating developing historic interpretive signage as one of its bicentennial projects. This project is on hold until the Committee decides on its program. No Update this quarter. A potential funding source has been identified to implement this project and staff is working with the River Restoration Task Force and Bicentennial Committee to define a specific project scope and prepare a funding request. March Update
|  |  |  | b. | Support the planning and implementation of a Bicentennial celebration | All | Cemetery and Bicentennial Committees continue to meet and staff provides assistance as needed. Staff has provide support to the Bicentennial committee with several of their interest areas. Communications staff met with the committee to discuss marketing the bicentennial; Director of Strategic Planning assisted the committee in submitting a grant for the Northville History Trail; DDA Director is assisting the committee in developing an donor acknowlegement plan.
|  |  |  | c. | Support the efforts of the Cemetery Committee | All | Staff met with Cemetery committee to discuss infrastructure needs and completed extensive tree trimming in support of the committee restoration efforts. Cemetery committee continues cleaning stones in Oakwood historical cemetery and are raising funds to conduct additional improvements. The committee is also pursuing estimates to replace the fencing. Staff has provide support to the Cemetery Committee as they pursue quotes and funding for new fencing. March Update
|  |  |  | d. | Support relocation of the Log Cabin | SP/ DPW | A site plan was provided to staff detailing the location and installation plans for the log cabin. Feedback was provided to the Historical Society and the final proposed site plan will be brought to the Planning Commission for review and approval in May. A coordination meeting was held on June 4 with representatives from HP, the River Park contractor, representatives from the Historical Society and city staff to discuss placement of the Log Cabin and coordinate the necessary tasks. The Planning Commission approved the Log Cabin site plan on June 17, and ongoing coordination is happening between HP and the Log Cabin team. Excavation and construction of the cabin foundation is expected in July. The basement has been excavated and poured for the Log Cabin and the cabin will be moved into place in October. The Log Cabin has been installed on its new foundation, water and sewer has been extended to the building, and a stone facing has been adhered to the foundation. Landscaping around the building and installation of an electrical connection is expected in spring, 2026. March Update
IV. | High Quality Environment: Environmental Sustainability
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Reduced environmental footprint | 1. | Utilize sustainable measures to manage and mitigate storm water in the City | a. | Evaluate options for monitoring soil erosion and sedimentation control measures in house | DPW/ CD | This program would likely be administered by the Community Development Department and will be evaluated during the user fee study. Staff is reviewing requirements for administering a soil erosion and sedimentation control (SESC) program. The user fee study provided proposed fees if this service is brought in-house. Staff has researched the training required, and is determining how to proceed. Code enforcement staff will begin SESC monitoring of construction projects within the city in February. Because Wayne County is the regulatory agency for SESC we are unable to recoup fees for this work at this time but expect existing staff to be able to absorb the additional task during routine site visits. March Update
|  | 2. | Implement energy conservation measures to reduce utility usage | a. | Conduct inspections of electrical panels in all facilities to ensure safe and efficient functioning | DPW | No progress this quarter No progress this quarter No progress this quarter Thermal graphic imaging contractor has been contacted to schedule and assessment. Thermal Graphic Imaging was completed on February 3 for City Hall, DPW and Allen Terrace. Minor issues were found and corrected.
|  |  |  | b. | Assess City Hall HVAC system to provide consistency in heating and cooling | DPW | The Maintenance Manager has been monitoring the HVAC system and adjusting controls as needed. A more comprehensive assessment is planned for the future. System monitoring is ongoing and deficiencies are corrected as they are identified. Some improvements are being realized. System monitoring is ongoing. There continue to be issues with unexplained temperature fluctuation. System monitoring is ongoing. March Update
B. | Integrated mobility network | 1. | Provide for safe multi-modal transportation throughout the City | a. | Develop a non-motorized facilities map identifying existing routes to popular community resources, including city parks and green spaces | SP | No progress this quarter This item is on hold until the City website is updated so the option of providing an on-line resource can be considered. This item remains on hold. No additional update this quarter March Update
IV. | High Quality Environment: Environmental Sustainability (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | b. | Complete installation of mid-block crossings associated with the Downs project (Shared Streets grant) | DPW/ SP | Council approved a consultant services contract with OHM to begin construction plan development for the project. The construction schedule will be coordinated with other local and regional road projects. No progress this quarter. The anticipated project schedule is to conduct design in the fall, bid letting and contract award in winter 2026, and construction in spring/summer 2026. No substantial progress to date. Project remains on schedule. Plans have been developed for the pedestrian crossings and submitted to Wayne County for review. Topographic data has been gathered and the design is being coordinated with other planned projects. We are tracking for a spring bid letting. March Update
C. | Environmental sustainability and resiliency | 1. | Provide for the conservation of natural resources through reduction and recycling | a. | Develop an informational piece of recycling resources. | DPW/ COM | No progress this quarter Staff is supporting the Sustainability Team in its public outreach efforts, including production of informational literature for use in public outreach. We are consistently sharing important pieces on out Facebook page. We are sharing important information on social media and the city newsletter. March Update
|  | 2. | Provide for environmental protection through appropriate programs and regulation | a. | Complete implementation of the FOG ordinance | DPW/ DDA | A letter to local business has been drafted indicating that the FOG ordinance will be enforced beginning July 1 and the grease dumpsters will be removed at that time. Letters were distributed to restaurant owners and the dumpsters are scheduled for removal. Grease Dumpster contractor has been notified to remove dumpsters The city's grease dumpster contractor, Mahoney Environmental, will be removing the dumpsters on March 1. They have contacted the remaining business who have not yet install on-site grease catchment systems to offer assistance so they are prepared for the grease dumpster removal. March Update
|  |  |  | b. | Evaluate programs for commercial refuse management including, repair or replace dumpsters, add dumpster locks, cameras, etc. | DPW/ DDA/ POL | Cameras have been installed to monitor the Mary Alexander Dumpsters. Additional cameras will be installed at other dumpster sites to monitor illegal dumping. Current Mary Alexander dumpster cameras had positive results. Further discussion would need to be had as to where and when the next camera or cameras will be placed. No update this quarter. March Update
IV. | High Quality Environment: Environmental Sustainability (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  | 3. | Identify important natural resources and provide for their protection and preservation | a. | Update the tree survey and tree maintenance program, and expand both to include all public properties | DPW/ SP | No update this quarter A proposal to do this work was requested from Davey Tree company. Staff is monitoring for grants for funding sources. Awaiting proposal from Davey Tree. Trees from The Downs landscape plan are being added to the city's GIS system and key trees identified in the Ford Field East Natural Features Inventory will also be added. Staff is also working with the Tree Champions to assist in identifying trees in the cemeteries March Update
|  |  |  | b. | Conduct a natural features inventory of Ford Field east | SP | The Michigan Natural Features Inventory (MNFI) has been contacted to provide a proposal for consideration. MNFI has been engaged to inventory the natural features of the site and have conducted the first of four site visits to the park. MNFI will visit site during each season and provide a report once completed. A Natural Features and Rare Species Assessment of Ford Field Park Ease has been received. The information in the final report will be used to in the development of the NRTF grant application and to guide trail design. COMPLETED
V. | Enhanced Public Assets: Transportation and Infrastructure
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Stable transportation infrastructure | 1. | Provide safe roads | a. | Evaluate the street asset management plan and provide recommendations to address system needs | DPW | No update this quarter The city received a draft plan from OHM and provided feedback. The report is being finalized. The next 3 years of improvements have been identified to coordinate with the water system improvements program. In progress OHM is reviewing and updating the 2024 Asset Management Plan, and will develop a street improvements program for review by city council in early 2026. March Update
|  |  |  | b. | Repair High Street culvert | DPW | $750,000 was received for this project from a special allocation through Senator Bayer's office. The grant agreement was approved by City Council in March. Options are being evaluated to fund the additional $500,000 needed for the project. A request for $1.2 million in Community Project Funding was submitted to Congresswoman Dingell's office for the additional funds needed for this project. The funding request was increased to reflect increases in project costs, and allow ample funding for engineering, any easement acquisition costs, and to provide a healthy contingency. Funding remains uncertain for Community Projects through the federal government. No additional information is available at this time. March Update
V. | Enhanced Public Assets: Transportation and Infrastructure (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | c. | Explore funding for roundabout and bridge at 7 Mile and Hines | DPW | A $2,185,665 grant has been received from SEMCOG for this project. Options are being evaluated to fund the City's $488,000 match as well as a bridge into the Downs development. Monitoring is ongoing for potential funding sources for bridge construction, engineering fees and the city's local match to the SEMCOG grant. There is no update this quarter. Continue monitoring for potential funding sources. March Update
|  |  |  | d. | Complete the replacement of the Rural Hill Bridge | DPW | Contract has been awarded by MDOT to Z-contracting, who has completed the tree removal. The bridge is expected to be closed Memorial Day to August 1. A 5' pedestrian path across the bridge will be maintained at all times and a communication campaign is being developed to notify family members, residents, and funeral homes of the bridge closure. Discussions are underway with local funeral homes to coordinate opening and closing operations. Construction began June 16 and is expected to be completed by mid-August. COMPLETE
|  |  |  | e. | Complete the construction of the Center/Sheldon/7-mile roundabout | DPW | Construction plans are complete and the necessary ROW changes have been made within Wayne County. Plans have been submitted to MDOT and a June bid-letting is anticipated. The roundabout project was let for bid in June and prices will be received on July 11. Mobilization is anticipated in late August, with construction lasting through Thanksgiving. The round-about construction is well underway. Bi-weekly updates are distributed through Constant Contact. The project is on schedule to be completed in November. The round-a-bout is substantially complete and has been opened for use. Street lights, pedestrian crossings, and permanent striping will be installed in the spring. March Update
|  |  |  | f. | Evaluate Cady Street re-routing proposal | DPW | No progress this quarter This project is on hold until a Foundry Flask redevelopment schedule is established. This project remains on hold. No additional information is available this quarter. March Update
V. | Enhanced Public Assets: Transportation and Infrastructure (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
B. | Reliable public services | 1. | Continue investments in neighborhood streets, water and sewer improvements | a. | Remove water system reservoir and implement water system adjustments to address system needs | DPW | $1,000,000 was received for this project from a special allocation through Senator Bayer's office. The grant contract was approved by City Council in March. The additional funds needed for the project will be provided by the water system improvements bond measure. Proposal were accepted from venders to provide a prepackaged booster station. A firm has been selected and their design is being incorporated into construction plans. It is anticipated that the project will be released for bid by the end of July with construction in 2026. The bid opening for the project was held in early September and Council awarded the construction contract mid-September. The project was under the engineers estimate. A pre-construction meeting is scheduled for October and a more detailed schedule will be available after that time. A contract was awarded to Sourcing Group in October. They have mobilized on site and are working on Phase I of the project which includes installation of a water main from the GLWA authority water main to the new booster station location, then to the water tower. This is a 3-year project. March Update
|  |  |  | b. | Reconstruct roads in coord. with other infrastructure improvements | DPW | No update this quarter The Eaton Drive reconstruction is being completed in conjunction with other infrastructure improvements. Bids were opened for the work on June 30, and a Contract recommendation is anticipated in July, for fall construction. The work includes road reconstruction and water main work. A $250,000 grant was received and will support the $1.5 million cost. Eaton Drive is under construction and progressing quickly. Eaton Road reconstruction has been substantially completed and has been reopened for use. The road has been reconstructed and water and sewer improvements completed. The first lift of asphalt has been laid installed. The final asphalt lift will be laid in the spring and restoration completed. Plans are underway for the complete reconstruction of River Street in FY27, including installation of curb and gutter, storm sewer and drain, and new water main. March Update
V. | Enhanced Public Assets: Transportation and Infrastructure (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  | 2. | Preserve existing drains and drainage infrastructure | a. | Review the 2024 culvert and bridge inspection report and recommend priorities | DPW | A program for culvert and bridge repair or replacement was developed as part of the 2026 Capital Projects plan and will be presented to City Council during the budget process. The Randolph Drain culvert below Millpond Court has been replaced and the Oakland County Water Resource Commissioners Office is evaluating the condition of the culvert beneath Center Street. The Center Street culvert is planned for repair in summer, 2026; the city is still awaiting results of the 2026 Community Funding request for the High Street Bridge; and the Randolph Drain project at Serenity Point is expected to be complete by Thanksgiving. Funds have been secured to mill and fill Center Street from 7-Mile to Lake Street, and to repair the portion of the drain culvert that is immediately below the street. This portion of the culvert repairs will be done in late summer, 2027. The section of the culvert on the west side of Center Street is not elegible for these grant funds and is in critical condition so that work will be completed in summer 2026 as a drainage district project. March Update
|  | 3. | Ensure optimum use of public facilities and right-of-ways | a. | Evaluate establishing an easement setback ordinance | CD | March Update
|  |  |  | b. | Explore legislative solution to ensure local governmental control of public right-of-ways | CM | March Update
C. | Quality public facilities | 1. | Preserve existing public facilities | a. | Compile a comprehensive capital projects plan | SP/ FIN | A comprehensive 6-year capital projects plan, including both funded and unfunded projects, has been developed as part of the 2026 Budget and will be presented to Council during the budget process. The updated capital project plan was presented to City Council on April 28 and was incorporated onto the FY2025-26 Budget document. COMPLETE
|  |  |  | b. | Update the Allen Terrace facility assessment. | AT | No update this quarter No update this quarter Began looking into various options and costs associated with replacing the Packaged Terminal Air Conditioning (PTAC) systems Continuing to look into various options for PTAC replacement. Researching cost effective window/sliding door replacements and grants to cover the cost. Special testing done to 1st floor bathrooms for possible renovations through a Wayne County CDBG grant March Update
V. | Enhanced Public Assets: Transportation and Infrastructure (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | c. | Develop a parking system maint. & capital needs program, including lots, structures, and funding recommendations | DDA/ DPW | No update this quarter No update this quarter No update this quarter December Update The parking system inventory was completed and an additional inspection of the parking structures was also completed. The information from these two reports has been incorporated into the Capital Improvements Plan. COMPLETED
|  | 2. | Ensure efficient use of existing facilities | a. | Improve existing facilities to provide efficient staff spaces | SP | No update this quarter A door and sidelights has been designed and ordered to enclose the DDA/Community Development office space. Consideration is being given to removing the plexiglass barriers surrounding the various lobby counters and the layout of the Code and Clerk's offices are being evaluated to determine if there are any space efficiencies that could be implemented. Prices have been secured to remove the plexiglass barriers and repair the safety gates protecting the lobby counters. This information is being evaluated and additional options are being researched. March Update
|  |  |  | b. | Update cemetery ordinances | SP | No update this quarter No update this quarter No update this quarter. A draft ordinance has been created and is under review by city attorney March Update
VI. | Enhanced Public Assets: Recreational and Cultural Opportunities
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Contemporary recreational facilities | 1. | Ensure visitors of all abilities can access recreation programs and facilities | a. | Complete Ford Field gateway and bank stabilization project | SP | Bids were opened for the project and options for design features were reviewed with Council on March 17. A Contract award recommendation will be provide to City Council on April 7. A construction contract was approved on April 7 and preconstruction meeting was held on May 30. Construction is expected to begin in late July/early August. DTE is scheduled to replace the power poles in July. Construction is underway and moving quickly. The sidewalk and fence along Hutton Street has been removed. The power poles have been replaced but the utility companies still need to move their lines to the new poles. The new accessible entry ramp has been grading behind Robert's Rock. The project is on schedule to be substantially completed by the end of the year. Construction continued this quarter. The sidewalk along Hutton Street was replaced, the decorative fencing has been installed and the ADA ramp into the park from Hutton Street has been graded. The retaining wall around Robert's Rock is installed and will be planted in the spring, and the pedestrian crossing signal near the Hutton and Dunlap Intersection is installed. A grant extension was secured from MEDC to allow additional time to complete the project in spring 2026, including construction of the overlook plaza and retaining wall. March Update
|  |  |  | b. | Replace Ford Field playground with an accessible structure | SP | The Patronicy fundraising campaign was launched on February 20, and over $57,000 in donations have been received. The Northville Rotary will launch an additional fundraising effort in May. Bids have been let for the sitework and playground construction, and are due on Thursday, April 10. Community input on the playground design will be sought in May. The Playground Team continues to review playground designs. City Council will be updated on the project in July. Spurlocks has been awarded a contract for the playground sitework and they removed the playground at the end of September. The pickets and plaques were salvaged for interested people to pick up. Weather permitting, site grading, and installation of the playground subbase and concrete walkways will all be completed this fall. The wooden playground has been removed and the site was excavated for the subbase and underdrainage system. Concrete edging as been installed as have the boulder seating and flagstone walkway. Work has stopped for the season and will resume in the spring. March Update
|  | 2. | Enhance visitor recreational experiences through infrastructure improvements | a. | Prepare the new Farmers Market site for use for the 2025 market season | CM | A Consortium has been established to oversee the Northville Commons/Farmers Market site and work is progressing on the site to prepare for the 2025 market season. The 2025 Farmer's Market season was opened on May 1 in the new permanent location. COMPLETE
VI. | Enhanced Public Assets: Recreational and Cultural Opportunities (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | b. | Complete the improvements to Serenity Point | SP | The first phase of the Serenity Point improvements, installation of the pools and weirs, has been completed. The second phase will be completed in June and includes extending the culvert, stabilizing the headwall, and removing the graffiti on the overflow. The culvert extension is planned to be installed in the fall. Staff is working with interested community members to develop a landscape restoration plan for the area. The culvert extension is anticipated to be installed in November. The culvert extension still needs to be installed and the project completed. There is no schedule at this time. March Update
|  |  |  | c. | Construct restrooms at Ford Field Park | SP | The source of funds for the restroom grant is the National Park Service. It is unclear at this time whether the changes in the Federal government will impact the funding program so no progress will be made on this project until further direction is received from the Grant Coordinator. The city received notification from the MDNR that the grant has been moved to an awarding officer for issuance of a grant agreement. There is currently no estimate on when the grant agreement will be available but this is good news and increases the probability that the grant will be funded. City Council approved the Land and Water Grant project agreement on August 18. Proposals have been accepted from design consultants for the project. Six firms expressed an interest in being considered. GMA was awarded a Consultant Services Contract for the project and design is underway. March Update
|  |  |  | d. | Monitor construction of the River Park and plan for its acceptance into the park system | SP | River Park construction continues with installation of toe wood, root balls and riffles in the central portion of the river. The features on the north and south side of the river channel won't be completed until the bridge abutments are installed. Information about the concrete box culvert demolition will be presented to City Council in April. The box culvert demolition was discussed by City Council on April 7. The east pedestrian bridge abutments have been successfully poured and once the concrete has cured, they will be waterproofed and finish grading will begin. 1,100 shade trees have been delivered to the site for planting in the park. Considerable progress has been made on the River Park construction. The box culvert is substantially demolished and approximately 800' of the river bed has been constructed and established. The west pedestrian bridge abutments have been poured. The pedestrian bridges are expected to arrive in October. Substantial portions of the River Park were completed this quarter, including installation of the two bridges, paving the first lift of asphalt on the pathways, and installation of the landscaping. Remaining items will be completed in the spring and the park conveyed to the City. March Update
VI. | Enhanced Public Assets: Recreational and Cultural Opportunities (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | e. | Monitor construction of Central Park and plan for its acceptance into the park system | SP | March Update
|  | 3 | Continue partnerships that support regional programs and services | a. | Jointly with Northville Township, develop a plan for improvements to Northville Commons that support operations of the Farmers Market | CM | March Update
|  |  |  | b. | Define a program with Northville Township to support community use of Northville Commons | CM/SP | March Update
|  |  |  | c. | Continue to explore options for addressing Library space needs with the Library Board | CM | March Update
B. | Responsive and responsible planning | 1. | Develop long-range plans to guide future improvements that reflect the community | a. | Develop a Northville Riverwalk Plan | SP | No update this quarter The riverwalk plan from 7-mile Road to Ford Field west continues to be refined through preparation of the Ford Field East TAP grant and discussion associated with the Foundry Flask property. The River Restoration Task force continues to further develop potential trail routes from Ford Field north to 8-Mile Road and further. As an extension of the TAP grant for the Ford Field East section of the river trail, OHM is developing a feasibility plan for the trail section through Foundry Flask and connecting to the DTE substation site. A preliminary trail layout through Foundry Flask was completed and discussions held with DTE to coordinate improvements on the Beal Substation site to include a trail connection. March Update
VI. | Enhanced Public Assets: Recreational and Cultural Opportunities (continued)
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
|  |  |  | b. | Develop expanded regional trail implementation plan | SP | No update this quarter Northville Township is implementing the 7-mile Pathway project this fall to expand access to the Hines Trail, and the city is planning installation of a mid-block pedestrian crossing at River Street in summer 2026 to make connection to the trails south of 7-mile easier and safer. Discussions continue with the Novi Mobility Network and the 9-Mile Pathway Task Force to promote regional trails and trail connections to the north. No further update this quarter City Council approved a memorandum of understanding to formalize the city's participation on the Nine Mile Pathway Task force and the Director of Strategic Planning will represent the city on the project. March Update
ABBREVIATION KEY
|  | Ref. | Department | Ref. | Department
|  | AT | Allen Terrace | DDA | Downtown Development Association
|  | CD | Community Development | DPW | Department of Public Works
|  | CK | Clerk | FIN | Finance
|  | CM | City Manager | POL | Police
|  | COM | Communications | SP | Strategic Planning and Special Projects